## Estimation (hidden)
Efforts for New Features and Changes in Wage work (in Hours)
Analysis Effort and Support | 9.23 | 10% of Development team's combined effort
Development | 71 | Detailed in the below grid
QA | 21.3 | 30% of the Development efforts
Project Management | 13.4616 | 5% of the whole project team
UAT Support (Staging or Client Environment) | 10.65 | 50% of the QA Effort
Warranty and Go-Live Support | 5.0765 | 5% of BA, QA and Development effort
Total Effort | 130.7181
Assumption
1. Effort for Reporting Changes are tentative in nature. There will be an assessment once we have the detailed discussion done
Following features are considered as the New and Changed Feature
Task Name | Features | Developemt Effort (IN hours)
To prepare the Opening Balance Screen | NEW | 1
To get the Details of the additional bank from the client, | NEW
Remove Payperiod and year selection on earning and deductions tab | changes | 1
Database schema for shift Master | New | 1
Employee Supervisor Mapping database changes | New | 8
Add permission for Employee supervisor mapping
Add Other bank in employee Tab and change in schema | New | 2
Add Refrence number in database schema | New | 2
Change employee update and create for all the APIs
add bulk import opening balance for employees | New | 8
Prepare the document | New
Change missing attendance according to supervisor | changes | 6
Company Level & Branch Level | New | 6
change payslip to include opening balance | New | 8
While run payroll calculate load EMI | New | 6
While run payroll calculate based on company and branch level set up | New | 6
Statutory Report PDF | New | 16
Salary JE report | New
Calculate Statutory Components : All report need csv format | New
Verify other reports as well. | New

## Updated Detailed Plan - All Spr
# | Sprint | Activity Name | Task ID | Detailed Task Name/Description | Dependency | Team Name | Owner | Start Date | End Date | Remarks
1 | Sprint 1 | Requiremet Gathering Sprint 1 |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-08 | 2025-12-10
2 |  | Documentation Sign Off Sprint 1 |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-10
3 |  | Requiremet Gathering Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-17
4 |  | Documentation Sign Off Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-17 | 2025-12-19
5 |  | FRD Walkthrough Call |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-10
6 |  | External Kick off slides |  | At project level |  | PM/PC | Ramyak Bhavsar | 2025-12-10 | 2025-12-10
7 |  | External Kick off meeting |  | At project level |  | PM/PC | Ramyak Bhavsar | 2025-12-10
8 |  | UAC review Call |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-11 | 2025-12-11
9 |  | Test strategy document |  | Sprint 1 |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-12
10 |  | Writing Testcases |  | User Management Role Management Department Management |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-12
11 |  | Testcases Review Call |  | User Management Role Management Department Management |  | QA | Siddhi Shukla | 2025-12-15 | 2025-12-15
14 |  | Department Management |  | Department Listing Add department functionlality |  | Developer | Yogesh Hadiya | 2025-12-11 | 2025-12-11
13 |  | Role Management |  | Role Listing Add new role flow Premission Matrix |  | Developer | Yogesh Hadiya | 2025-12-12 | 2025-12-15
12 |  | User Management |  | Add user flow logic |  | Developer | Yogesh Hadiya | 2025-12-16 | 2025-12-16
15 |  | Code Review |  | Code Review |  | TL | Jeshal Kalena | 2025-12-12 | 2025-12-17
16 |  | Testing |  | Scope Sprint 1 |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-18
17 |  | Bug Fixing |  | Scope Sprint 1 |  | Developer | Jeshal Kalena | 2025-12-12 | 2025-12-18
18 |  | Testing Sign Off mail |  | Sprint 1 |  | QA | Siddhi Shukla | 2025-12-19 | 2025-12-19
19 |  | Sprint Progress Report |  | Sprint 1 |  | PM/PC | Ramyak Bhavsar | 2025-12-19 | 2025-12-19
20 |  | Internal Demo |  | Sprint 1 |  | PM/PC | Ramyak Bhavsar | 2025-12-19 | 2025-12-19
21 |  | UAT Testing/Sign off |  | User Management Role Management Department Management |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22 | Can be delayed because client is not available and we need to wait for the client's availability.
22 |  | External Demo |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22
23 |  | Sprint Release Note |  | User Management Role Management Department Management |  | QA, BA | Shubham Vyas | 2025-12-22 | 2025-12-22
24 |  | Retrospective |  | Sprint Retrospective |  | PM/PC | Ramyak Bhavsar | 2025-12-23 | 2025-12-23
Sprint 2 |  |  | Sprint 2
# | Sprint | Activity Name | Task ID | Detailed Task Name/Description | Dependency | Team Name | Owner | Start Date | End Date
1 | Sprint 1 | Requiremet Gathering Sprint 1 |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-08 | 2025-12-10
2 |  | Documentation Sign Off Sprint 1 |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-10
3 |  | Requiremet Gathering Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-17
4 |  | Documentation Sign Off Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-17 | 2025-12-19
5 |  | FRD Walkthrough Call |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-10
6 |  | External Kick off slides |  | At project level |  | PM/PC | Ramyak Bhavsar | 2025-12-10 | 2025-12-10
7 |  | External Kick off meeting |  | At project level |  | PM/PC | Ramyak Bhavsar | 2025-12-10
8 |  | UAC review Call |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-11 | 2025-12-11
9 |  | Test strategy document |  | Sprint 1 |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-12
10 |  | Writing Testcases |  | User Management Role Management Department Management |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-12
11 |  | Testcases Review Call |  | User Management Role Management Department Management |  | QA | Siddhi Shukla | 2025-12-15 | 2025-12-15
14 |  | Department Management |  | Department Listing Add department functionlality |  | Developer | Yogesh Hadiya | 2025-12-11 | 2025-12-11
13 |  | Role Management |  | Role Listing Add new role flow Premission Matrix |  | Developer | Yogesh Hadiya | 2025-12-12 | 2025-12-15
12 |  | User Management |  | Add user flow logic |  | Developer | Yogesh Hadiya | 2025-12-16 | 2025-12-16
15 |  | Code Review |  | Code Review |  | TL | Jeshal Kalena | 2025-12-12 | 2025-12-17
16 |  | Testing |  | Scope Sprint 1 |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-18
17 |  | Bug Fixing |  | Scope Sprint 1 |  | Developer | Jeshal Kalena | 2025-12-12 | 2025-12-18
18 |  | Testing Sign Off mail |  | Sprint 1 |  | QA | Siddhi Shukla | 2025-12-19 | 2025-12-19
19 |  | Sprint Progress Report |  | Sprint 1 |  | PM/PC | Ramyak Bhavsar | 2025-12-19 | 2025-12-19
20 |  | Internal Demo |  | Sprint 1 |  | PM/PC | Ramyak Bhavsar | 2025-12-19 | 2025-12-19
21 |  | UAT Testing/Sign off |  | User Management Role Management Department Management |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22
22 |  | External Demo |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22
23 |  | Sprint Release Note |  | User Management Role Management Department Management |  | QA, BA | Shubham Vyas | 2025-12-22 | 2025-12-22
24 |  | Retrospective |  | Sprint Retrospective |  | PM/PC | Ramyak Bhavsar | 2025-12-23 | 2025-12-23

## Detailed Plan - All Sprints
# | Sprint | Activity Name | Task ID | Detailed Task Name/Description | Dependency | Team Name | Owner | Start Date | End Date
1 | Sprint 1 | Requirement Gathering Sprint 1 |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-08 | 2025-12-10
2 |  | Documentation Sign Off Sprint 1 |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-10
3 |  | Requirement Gathering Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-16
4 |  | Documentation Sign Off Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-16 | 2025-12-17
5 |  | FRD Walkthrough Call |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-10 | 2025-12-10
6 |  | External Kick off slides |  | At project level |  | PM/PC | Ramyak Bhavsar | 2025-12-10 | 2025-12-10
7 |  | External Kick off meeting |  | At project level |  | PM/PC | Ramyak Bhavsar | 2025-12-10
8 |  | UAC review Call |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-11 | 2025-12-11
9 |  | Test strategy document |  | Sprint 1 |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-12
10 |  | Writing Testcases |  | User Management Role Management Department Management |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-12
11 |  | Testcases Review Call |  | User Management Role Management Department Management |  | QA | Siddhi Shukla | 2025-12-15 | 2025-12-15
14 |  | Department Management |  | Department Listing Add department functionlality |  | Developer | Yogesh Hadiya | 2025-12-11 | 2025-12-11
13 |  | Role Management |  | Role Listing Add new role flow Permission Matrix |  | Developer | Yogesh Hadiya | 2025-12-12 | 2025-12-15
12 |  | User Management |  | Add user flow logic |  | Developer | Yogesh Hadiya | 2025-12-16 | 2025-12-16
15 |  | Code Review |  | Code Review |  | TL | Jeshal Kalena | 2025-12-12 | 2025-12-17
16 |  | Testing |  | Scope Sprint 1 |  | QA | Siddhi Shukla | 2025-12-12 | 2025-12-18
17 |  | Bug Fixing |  | Scope Sprint 1 |  | Developer | Jeshal Kalena | 2025-12-12 | 2025-12-18
18 |  | Testing Sign Off mail |  | Sprint 1 |  | QA | Siddhi Shukla | 2025-12-19 | 2025-12-19
19 |  | Sprint Progress Report |  | Sprint 1 |  | PM/PC | Ramyak Bhavsar | 2025-12-19 | 2025-12-19
20 |  | Internal Demo |  | Sprint 1 |  | PM/PC | Ramyak Bhavsar | 2025-12-19 | 2025-12-19
21 |  | UAT Testing/Sign off |  | User Management Role Management Department Management |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22
22 |  | External Demo |  | Sprint 1 |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22
23 |  | Sprint Release Note |  | User Management Role Management Department Management |  | QA, BA | Shubham Vyas | 2025-12-22 | 2025-12-22
24 |  | Retrospective |  | Sprint Retrospective |  | PM/PC | Ramyak Bhavsar | 2025-12-23 | 2025-12-23
Sprint 2 |  |  | Sprint 2
1 | Sprint 2 | Requirement Gathering Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-17 | 2025-12-19
2 |  | Documentation Sign Off Sprint 2 |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-19 | 2025-12-22
3 |  | Requirement Gathering Sprint 3 |  | Sprint 3 |  | BA | Shubham Vyas | 2025-12-22 | 2026-01-01
4 |  | Documentation Sign Off Sprint 3 |  | Sprint 3 |  | BA | Shubham Vyas | 2026-01-02 | 2026-01-05
5 |  | FRD Walkthrough Call |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-22 | 2025-12-22
6 |  | External Kick Off slides |  | At project level |  | PM/PC | Ajay Thakkar | 2025-12-22
7 |  | External Kick Off meeting |  | At project level |  | PM/PC | Ajay Thakkar | 2025-12-22
8 |  | UAC Review Call |  | Sprint 2 |  | BA | Shubham Vyas | 2025-12-23 | 2025-12-23
9 |  | Test strategy document |  | Sprint 2 |  | QA | Siddhi Shukla | 2025-12-23 | 2025-12-23
10 |  | Writing Testcases |  | Purchase Order |  | QA | Siddhi Shukla | 2025-12-24 | 2025-12-24
11 |  | Testcases Review Call |  | Purchase Order Listing / Filter Generate Purchase Order View/Edit/Delete Purchase Order Approve Purchase Order |  | QA | Siddhi Shukla | 2025-12-24 | 2025-12-24
14 |  | Purchase Order |  | Purchase Order Listing / Filter Generate Purchase Order View/Edit/Delete Purchase Order Approve Purchase Order |  | Developer | Yogesh Hadiya | 2025-12-24 | 2025-12-31
|  | Window Services |  | Fetch data from xero for all organizations, Chart of Accounts & Suppliers and Dump into database at everyday midnight |  | Developer | Yogesh Hadiya | 2025-12-23 | 2025-12-23
15 |  | Code Review |  | Code Review |  | TL | Jeshal Kalena | 2025-12-23 | 2025-12-31
16 |  | Testing |  | Scope Sprint 2 |  | QA | Siddhi Shukla | 2025-12-25 | 2026-01-02
17 |  | Bug Fixing |  | Scope Sprint 2 |  | Developer | Yogesh Hadiya | 2026-01-01 | 2026-01-02
18 |  | Testing Sign Off Mail |  | Sprint 2 |  | QA | Siddhi Shukla | 2026-01-05 | 2026-01-05
19 |  | Sprint Progress Report |  | Sprint 2 |  | PM/PC | Ajay Thakkar, Ramyak Bhavsar | 2026-01-05 | 2026-01-05
20 |  | Internal Demo |  | Sprint 2 |  | PM/PC | Ajay Thakkar, Ramyak Bhavsar | 2026-01-05 | 2026-01-05
21 |  | UAT Testing/Sign off |  | Purchase Order Listing / Filter Generate Purchase Order View/Edit/Delete Purchase Order Approve Purchase Order |  | BA | Shubham Vyas | 2026-01-06 | 2026-01-06
22 |  | External Demo |  | Sprint 2 |  | BA | Shubham Vyas | 2026-01-06 | 2026-01-06
23 |  | Sprint Release Note |  | Purchase Order Listing / Filter Generate Purchase Order View/Edit/Delete Purchase Order Approve Purchase Order |  | PM/PC | Ramyak Bhavsar | 2026-01-06 | 2026-01-06
24 |  | Retrospective |  | Sprint Retrospective |  | PM/PC | Ajay Thakkar, Ramyak Bhavsar | 2026-01-07 | 2026-01-07

## Detailed Plan - Sprint - 3
# | Sprint | Activity Name | Task ID | Detailed Task Name/Description | Dependency | Team Name | Owner | Start Date | End Date
1 | Sprint - 3 | Requirement Gathering Sprint 4 |  | Sprint 4 |  | BA | Shubham Vyas | 2026-01-08 | 2026-01-12
2 |  | Documentation Sign Off Sprint 4 |  | Sprint 4 |  | BA | Shubham Vyas | 2026-01-12 | 2026-01-12
3 |  | FRD Walkthrough Call |  | Sprint 3 |  | BA | Shubham Vyas | 2026-01-06 | 2026-01-06
4 |  | External Kick off slides |  | At project level |  | PM/PC | Ajay Thakkar | 2026-01-08 | 2026-01-08
5 |  | External Kick off meeting |  | At project level |  | PM/PC | Ajay Thakkar | 2026-01-08 | 2026-01-08
6 |  | UAC review Call |  | Sprint 3 |  | BA | Shubham Vyas | 2026-01-08 | 2026-01-08
7 |  | Test strategy document |  | Sprint 3 |  | QA | Siddhi Shukla | 2026-01-08 | 2026-01-09
8 |  | Test Cases |  | List Docs View/Assign POs OCR View Invoice and Dockets |  | QA | Siddhi Shukla | 2026-01-09 | 2026-01-12
9 |  | Testcases Review Call |  | List Docs View/Assign POs OCR View Invoice and Dockets |  | QA | Siddhi Shukla | 2026-01-12 | 2026-01-12
10 |  | Development Work |  | List Docs View/Assign POs OCR View Invoice and Dockets |  | Developer | Yogesh Hadiya | 2026-01-08 | 2026-01-27
11 |  | Code Review |  | Code Review |  | TL | Jeshal Kalena | 2026-01-09 | 2026-01-27
12 |  | Testing |  | Scope Sprint 3 |  | QA | Siddhi Shukla | 2026-01-12 | 2026-01-29
13 |  | Bug Fixing |  | Scope Sprint 3 |  | Developer | Jeshal Kalena | 2026-01-28 | 2026-01-28
14 |  | Testing Sign Off mail |  | Sprint 3 |  | QA | Siddhi Shukla | 2026-01-28 | 2026-01-28
15 |  | Sprint Progress Report |  | Sprint 3 |  | PM/PC | Ajay Thakkar | 2026-01-28 | 2026-01-28
16 |  | Internal Demo |  | Sprint 3 |  | PM/PC | Ajay Thakkar | 2026-01-28 | 2026-01-28
17 |  | UAT Testing/Sign off |  | List Docs View/Assign POs OCR View Invoice and Dockets |  | BA | Shubham Vyas | 2026-01-30 | 2026-02-02
18 |  | External Demo |  | Sprint 3 |  | BA | Shubham Vyas | 2026-02-02 | 2026-02-02
19 |  | Sprint Release Note |  | List Docs View/Assign POs OCR View Invoice and Dockets |  | QA, BA | Shubham Vyas | 2026-02-02 | 2026-02-02
20 |  | Retrospective |  | Sprint Retrospective |  | PM/PC | Ajay Thakkar | 2026-02-03 | 2026-02-03

## Detailed Plan - Sprint - 4
# | Sprint | Activity Name | Task ID | Detailed Task Name/Description | Dependency | Team Name | Owner | Start Date | End Date
3 |  | FRD Walkthrough Call |  | Sprint 4 |  | BA | Shubham Vyas | 2026-01-29 | 2026-01-29
4 |  | External Kick off slides |  | At Project level |  | PM/PC | Ajay Thakkar | 2026-01-29 | 2026-01-29
5 |  | External Kick off meeting |  | At Project level |  | PM/PC | Ajay Thakkar | 2026-01-29 | 2026-01-29
6 |  | UAC review Call |  | Sprint 4 |  | BA | Shubham Vyas | 2026-01-30 | 2026-01-30
7 |  | Test strategy document |  | Sprint 4 |  | QA | Siddhi Shukla | 2026-02-02 | 2026-02-02
8 |  | Test Cases |  | Matching Screens Post Data To XERO Reports |  | QA | Siddhi Shukla | 2026-02-02 | 2026-02-02
9 |  | Testcases Review Call |  | Matching Screens Post Data To XERO Reports |  | QA | Siddhi Shukla | 2026-02-02 | 2026-02-02
10 |  | Development Work |  | Matching Screens Post Data To XERO Reports |  | Developer | Yogesh Hadiya | 2026-01-29
11 |  | Code Review |  | Code Review |  | TL | Jeshal Kalena
12 |  | Testing |  | Matching Screens Post Data To XERO Reports |  | QA | Siddhi Shukla
13 |  | Bug Fixing |  | Matching Screens Post Data To XERO Reports |  | Developer | Jeshal Kalena
14 |  | Testing Sign Off mail |  | Sprint 4 |  | QA | Siddhi Shukla
15 |  | Sprint Progress Report |  | Sprint 4 |  | PM/PC | Ajay Thakkar
16 |  | Internal Demo |  | Sprint 4 |  | PM/PC | Ajay Thakkar
17 |  | UAT Testing/Sign off |  | Matching Screens Post Data To XERO Reports |  | BA | Shubham Vyas
18 |  | External Demo |  | Sprint 4 |  | BA | Shubham Vyas
19 |  | Sprint Release Note |  | Sprint 4 |  | QA, BA | Shubham Vyas
20 |  | Retrospective |  | Sprint Retrospective |  | PM/PC | Ajay Thakkar

## Project RoadMap
Proposed Tentative Schedule
Features |  | December |  |  |  | 2025-01-26 |  |  |  | 2025-02-26 |  |  |  | 2025-03-26
|  | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1
Sprint 1 | Department Management Role Management User Management Deployment Staging UAT Testing | December W2: Demo: 23 December 2025
Sprint 1 UAT |  | December W4: 2026-01-08
Sprint 2 | Purchase Order Discrepency management [Matching Logic] Deployment Staging UAT Testing | December W4: 2026-01-08
Sprint 2 UAT |  | 2025-01-26 W1: 2026-01-30
Sprint 3 | Dropbox integration Azure OCR Extraction Assign PO Deployment Staging UAT Testing | 2025-01-26 W1: 2026-01-30
Sprint 3 UAT |  | 2025-02-26 W1: 2026-02-16
Sprint 4 | Reports Matching logic Audit Log Infra & Deployment Deployment Staging UAT Testing | 2025-02-26 W1: 2026-02-16
Sprint 4 UAT |  | 2025-02-26 W1: 2026-02-16
Warranty Support |  | 2025-02-26 W2: 2026-03-16

## Gantt Chart
|  |  |  | November |  |  |  |  | November | [14 empty] | December
c |  |  |  | Week 1 |  |  | Week 2 |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 3 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5
Task No. | Activity Name | Start Date | End Date | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2025-12-31
Sprint 1 | Requiremet Gathering Sprint 1 | 2025-12-08 | 2025-12-10
| Documentation Sign Off Sprint 1 | 2025-12-10 | 2025-12-10
| Requiremet Gathering Sprint 2 | 2025-12-10 | 2025-12-16
| Documentation Sign Off Sprint 2 | 2025-12-16 | 2025-12-17
| FRD Walkthrough Call | 2025-12-10 | 2025-12-10
| External Kick off slides | 2025-12-10 | 2025-12-10
| External Kick off meeting | 2025-12-10
| UAC review Call | 2025-12-11 | 2025-12-11
| Test strategy document | 2025-12-12 | 2025-12-12
| Writing Testcases | 2025-12-12 | 2025-12-12
| Testcases Review Call | 2025-12-15 | 2025-12-15
| Department Management | 2025-12-11 | 2025-12-11
| Role Management | 2025-12-12 | 2025-12-15
| User Management | 2025-12-16 | 2025-12-16
| Code Review | 2025-12-12 | 2025-12-17
| Testing | 2025-12-12 | 2025-12-18
| Bug Fixing | 2025-12-12 | 2025-12-18
| Testing Sign Off mail | 2025-12-19 | 2025-12-19
| Sprint Progress Report | 2025-12-19 | 2025-12-19
| Internal Demo | 2025-12-19 | 2025-12-19
| UAT Testing/Sign off | 2025-12-22 | 2025-12-22
| External Demo | 2025-12-22 | 2025-12-22
| Sprint Release Note | 2025-12-22 | 2025-12-22
| Retrospective | 2025-12-23 | 2025-12-23

## Detail Plan (hidden)
# | Sprint | Activity Name | Task ID | Detailed Task Name/Description | Dependency | Team Name | Owner | Start Date | End Date
1 | Sprint 5 | Documentation of the New Change Features |  | 1. AI OCR Time Logs 2. Loan Request Integration FCB 3. Mid Month Pay Integration FCB 4. Original Supervisor Feasibility |  | BA | Shivam Vyas | 2025-10-09 | 2025-10-09 | Sprint 5 | 2025-10-01 | 2025-10-17
2 |  | Preparing Screens |  | Preparing Screens For: 1. Loan Request Integration FCB 2. Mid Month Pay Integration FCB 3. Original Supervisor Feasibility |  | BA | Shivam Vyas | 2025-10-09 | 2025-10-09 | Sprint 6 | 2025-10-27 | 2025-11-07
3 |  | NAPSA Integration |  | Clarifications on the NAPSA Team |  | BA | Shivam Vyas | 2025-10-09 | 2025-10-17
4 |  | Documentation Sign Off |  | Documentation Sign Off | Client | BA | Shivam Vyas | 2025-10-10 | 2025-10-10 | Sprint 7 | 2025-11-10 | 2025-11-21
5 |  | BA UAC Review |  | BA UAC call sprint 5 |  | BA | Shivam Vyas | 2025-10-11 | 2025-10-11
6 |  | AI Based Time Logs Management OCR (Azure AI) |  | 1. Download template for supervisor wise. 2. upload the donwload timelog template after fill up 3. Using azure Document AI extract the timelog data for each employee. 4. provide preview of upload timelog. with client side paging and filters 5. submit the timelog for supervisor employees |  | Developer | Mansi Singh, Keval Soni | 2025-10-08 | 2025-10-10
7 |  | Mid Month Payment Integration Via Bank |  | 1 .create an modal that shows all the employees information 2. Create an modal that display the bank information 3. Create an api that fetches the employee information from the csv file of mid month 4. Initiate payment via FCB bank for employees 5 . maintain logs for each employee via mid month |  | Developer | Mansi Singh, Keval Soni | 2025-10-13 | 2025-10-15
8 |  | QA Writing Testcases |  | Writing testcases Sprint 5 |  | QA | Unnati Pandit. | 2025-10-13 | 2025-10-13
9 |  | Testcases Review Call |  | Review call with the development team for sprint 5 |  | QA | Unnati Pandit. | 2025-10-14 | 2025-10-14
10 |  | Quattro Support |  | Necessary Support to Quttro Payroll run |  | QA, BA, Developer | Shivam Vyas | 2025-10-08 | 2025-10-17
11 |  | Original Supervisor Functionality (Fallout Task) |  | Change schema to have original supervisor Add flow of disabling logs to new supervisor Change UI to add new column |  | Developer | Keval Soni, Mansi Singh | 2025-10-10 | 2025-10-17
12 |  | Quattro Payroll run |  | Necessary Support to Quttro Payroll run |  | Developer, BA, QA | Shivam Vyas | 2025-10-10 | 2025-10-17
13 |  | QA Testing |  | Scope : Feature of Sprint 5 |  | QA | Unnati Pandit. | 2025-10-27 | 2025-10-28
14 |  | Bug Fixing |  | Bug Fixing time for sprint 5 if any found |  | Developer | Mansi Singh | 2025-10-27 | 2025-10-28
15 |  | Regression Testing |  | Sanity testing for sprint 5 |  | QA | Unnati Pandit. | 2025-10-29 | 2025-10-30
16 | Sprint 6 | Internal Demo |  | Scope : 1. AI Based Time Logs Management OCR (Azure AI) 2.Mid Month Payment Integration Via Bank 3.Loan Payment Integration Via Bank |  | QA | Unnati Pandit. | 2025-10-29 | 2025-10-29
17 |  | BA Unit Testing |  | Scope : Feature of Sprint 5 | Internal Demo | BA | Shivam Vyas | 2025-10-30 | 2025-10-30
18 |  | External Demo |  | Scope : 1. AI Based Time Logs Management OCR (Azure AI) 2.Mid Month Payment Integration Via Bank 3.Loan Payment Integration Via Bank |  | BA | Shivam Vyas | 2025-10-31 | 2025-10-31
19 |  | UAT Testing |  | Scope : Feature of Sprint 5 |  | Client | Shruti | 2025-10-31 | 2025-11-03
20 |  | Production Release |  | Scope : Feature of Sprint 5 | UAT Testing | Developer | Keval Soni | 2025-11-04 | 2025-11-04
21 |  | Go Live Support |  | Scope : Feature of Sprint 5 |  | BA | Shivam Vyas | 2025-11-04 | 2025-11-04
22 |  | Requiremet Gathering |  | Adding & Mapping of COA --> Feature to add and map the Charts of Accounts. Superadmin Access --> Feature to SuperAdmin role it should be able to access any company from the Superadmin login screen Default Settings for the Statutory Components --> Whenever Super admin add any new company, there should be default settings to the statutory components to be applied. Employee Upload --> We need to show the number of times the Emp file uploaded. Automatically add Pay Group --> Feature to add the paygroup automatically when the new Employee is added. | Not Done? | BA | Shivam Vyas | 2025-10-27 | 2025-11-03
23 |  | Documentation Sign Off |  | Adding & Mapping of COA --> Feature to add and map the Charts of Accounts. Superadmin Access --> Feature to SuperAdmin role it should be able to access any company from the Superadmin login screen Default Settings for the Statutory Components --> Whenever Super admin add any new company, there should be default settings to the statutory components to be applied. Employee Upload History --> We need to show the number of times the Emp file uploaded. Automatically add Pay Group --> Feature to add the paygroup automatically when the new Employee is added. | Client | BA | Shivam Vyas | 2025-11-03 | 2025-11-03
24 |  | BA UAC Review |  | BA UAC call sprint 6 |  | BA | Shivam Vyas | 2025-11-04 | 2025-11-04
25 |  | QA writing test cases |  | Writing testcases Sprint 6 |  | QA | Unnati Pandit. | 2025-11-04 | 2025-11-04
26 |  | QA Test cases review call |  | Review call of the testcases for sprint 6 |  | QA | Unnati Pandit. | 2025-11-05 | 2025-11-05
27 |  | Quattro Support |  | Necessary Support to Quttro Payroll run |  | QA, BA, Developer | Shivam Vyas | 2025-10-17 | 2025-10-30
|  | Leave Pay and Gratutity Pay |  | 1. Add new column to opening balance named as add to current payroll. 2. Add logic to save column to db. 3. change LP& GP Schema to handle branchwise and separate LP & GP. 4. Do the migration to store new column data. 5, Add Logic to handle separate skip for the LP & GP. 6. Change Leave pay & Leave day in payslip. 7. Add Opening balance's column logic to 4th step. 8. Change UI of 4th step to have separate LP & GP. |  | Developer | Keval Soni, Mansi Singh | 2025-10-28 | 2025-10-31
|  | BA UAC Review LP & GP |  | Leave Pay and Gratutity Pay |  | BA | Shivam Vyas | 2025-10-28 | 2025-10-28
|  | Test Cases Writing and Walthrough |  | Leave Pay and Gratutity Pay |  | QA | Unnati Pandit. | 2025-10-28 | 2025-10-28
30 |  | Loan Request Integration FCB |  | 1 Employee submits loan request (amount, installments, notes). 2 System sets status to Pending for Approval. 3 Admin reviews request details (Employee ID/Name, Amount, Installments, Notes). 4 Admin approves with effective date & selects payment method (Cash/Bank). 5 On approval, status changes to Approved by Accounts. 6 If Cash, “Initiate Payment” stays disabled. 7 If Bank, admin clicks Initiate Payment. 8 Select company bank account filtered by employee currency. 9 Show payment Preview screen and confirm. 10 On success, set status to Loan Credited; lock edits to admins only. 11 Bulk payment for multiple employees (same currency only). 12 Export loan list to CSV (includes status, employee details, bank account number). 13 Provide list filters by Payment Method, Currency, Status. | BA KT Is not done | Developer | Mansi Singh, Keval Soni | 2025-11-03 | 2025-11-05
31 |  | QA Testing |  | Scope : Feature of Sprint 6 |  | QA | Unnati Pandit. | 2025-10-27 | 2025-11-06
32 |  | Bug Fixing |  | Bug Fixing time for sprint 6 if any found |  | Developer | Keval Soni, Mansi Singh | 2025-11-05 | 2025-11-06
33 |  | Regression Testing |  | Sanity testing for sprint 6 |  | QA | Unnati Pandit. | 2025-11-05 | 2025-11-05
34 | Sprint 7 | Internal Demo |  | Scope : 1. Leave Pay & Gratuity Pay 2.Original Supervisor Functionality (Fallout Task) 3.Loan Request Integration FCB |  | QA | Unnati Pandit. | 2025-11-06 | 2025-11-06
35 |  | BA UAT Testing |  | Scope : Feature of Sprint 6 | Internal Demo | BA | Shivam Vyas | 2025-11-07 | 2025-11-07
36 |  | External Demo |  | Scope : 1.Leave Pay and Gratutiy Pay 2.Loan Request Integration FCB |  | BA | Shivam Vyas | 2025-11-07 | 2025-11-07
37 |  | UAT Testing |  | Scope : Feature of Sprint 6 |  | Client | Shruti, Mitisha | 2025-11-07 | 2025-11-08
38 |  | Production Release |  | Scope : Feature of Sprint 6 | UAT Testing | Developer | Keval Soni | 2025-11-10 | 2025-11-10
39 |  | Go Live Support |  | Scope : Feature of Sprint 6 |  | BA | Shivam Vyas | 2025-11-10 | 2025-11-10
40 |  | Requiremet Gathering |  | Sprint 8 To be discussed |  | BA, Client | Shivam Vyas, Mitisha | 2025-11-10 | 2025-11-20
41 |  | Documentation Sign Off |  | Sprint 8 To be discussed | Client | BA | Shivam Vyas, Mitisha | 2025-11-21 | 2025-11-21
42 |  | BA UAC Call |  | BA UAC call sprint 7 |  | BA | Unnati Pandit., Shivam Vyas | 2025-11-11 | 2025-11-11
43 |  | QA Writing Testcases |  | Writing testcases Sprint 7 |  | QA | Unnati Pandit. | 2025-11-11 | 2025-11-11
44 |  | QA Testcases Review Call |  | Review call of the testcases for sprint 7 |  | QA | Unnati Pandit. | 2025-11-12 | 2025-11-12
28 |  | NAPSA Integration |  | Clarifications on the NAPSA Team |  | Developer | Mansi Singh, Keval Soni | 2025-11-18 | 2025-11-20
45 |  | Adding & Mapping of COA |  | Feature to add and map the Charts of Accounts. |  | Developer | Keval Soni, Mansi Singh | 2025-11-11 | 2025-11-18
46 |  | Superadmin Access |  | Feature to SuperAdmin role it should be able to access any company from the Superadmin login screen |  | Developer | Keval Soni, Mansi Singh | 2025-11-19 | 2025-11-19
47 |  | Default Settings for the Statutory Components |  | Whenever Super admin add any new company, there should be default settings to the statutory components to be applied. |  | Developer | Mansi Singh | 2025-11-11 | 2025-11-12
48 |  | Employee Upload History |  | We need to show the number of times the Emp file uploaded. |  | Developer | Mansi Singh | 2025-11-13 | 2025-11-13
49 |  | Automatically add Pay Group |  | Feature to add the paygroup automatically when the new Employee is added. |  | Developer | Mansi Singh | 2025-11-14 | 2025-11-14
50 |  | QA Testing |  | Scope : Feature of Sprint 7 |  | QA | Unnati Pandit. | 2025-11-11 | 2025-11-20
51 |  | Bug Fixing |  | Bug Fixing time for sprint 7 if any found |  | Developer | Keval Soni, Mansi Singh | 2025-11-19 | 2025-11-20
52 |  | BA UAT Testing |  | Scope : Feature of Sprint 7 |  | BA | Shivam Vyas | 2025-11-20 | 2025-11-20
53 |  | Regression Testing |  | Sanity testing for sprint 7 |  | QA | Unnati Pandit. | 2025-11-20 | 2025-11-20
54 |  | Internal Demo |  | Scope : 1.Adding & Mapping of COA 2.Superadmin Access 3. Employee Upload History 4. Automatically add Pay Group |  | QA | Unnati Pandit. | 2025-11-20 | 2025-11-20
55 |  | BA UAT Testing |  | Scope : Feature of Sprint 7 | Internal Demo | BA | Shivam Vyas | 2025-11-20 | 2025-11-21
56 |  | External Demo |  | Scope : 1.Adding & Mapping of COA 2.Superadmin Access 3. Employee Upload History 4. Automatically add Pay Group |  | BA | Shivam Vyas | 2025-11-21 | 2025-11-21
57 |  | UAT Testing |  | Scope : Feature of Sprint 7 |  | Client | Mitisha, Shruti | 2025-11-24 | 2025-11-25
58 |  | Production Release |  | Scope : Features of Sprint 7 | UAT Testing | Developer | Keval Soni | 2025-11-26 | 2025-11-26
59 |  | Go Live Support |  | Scope : Features of Sprint 7 |  | BA | Shivam Vyas | 2025-11-26 | 2025-11-26
60 |  | Client Feedback Quattro |  |  |  | Client, BA, PM Team | Mitisha, Shruti, Shivam Vyas
61 |  | Warranty Support |  | Warranty Support |  | BA, QA | Shivam Vyas, Unnati Pandit. | 2025-11-27 | 2025-12-16

## Gantt Chart (hidden)
|  |  |  | October | [22 empty] | November | [19 empty] | December
WageWorks Project Plan |  |  |  | Week 1 |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
Task No. | Activity Name | Start Date | End Date | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16
Sprint 5 | Documentation of the New Change Features | 2025-10-09 | 2025-10-09
| Preparing Screens | 2025-10-09 | 2025-10-09
| NAPSA Integration | 2025-10-09 | 2025-10-17
| Documentation Sign Off | 2025-10-10 | 2025-10-10
| BA UAC Review | 2025-10-11 | 2025-10-11
| AI Based Time Logs Management OCR (Azure AI) | 2025-10-08 | 2025-10-10
| Mid Month Payment Integration Via Bank | 2025-10-13 | 2025-10-15
| QA Writing Testcases | 2025-10-13 | 2025-10-13
| Testcases Review Call | 2025-10-14 | 2025-10-14
| Quattro Support | 2025-10-08 | 2025-10-17
| Original Supervisor Functionality (Fallout Task) | 2025-10-10 | 2025-10-17
| Quattro Payroll run | 2025-10-10 | 2025-10-17
| QA Testing | 2025-10-27 | 2025-10-28
| Bug Fixing | 2025-10-27 | 2025-10-28
| Regression Testing | 2025-10-29 | 2025-10-30
Sprint 6 | Internal Demo Sprint 5 | 2025-10-29 | 2025-10-29
| BA Unit Testing Sprint 5 | 2025-10-30 | 2025-10-30
| External Demo Sprint 5 | 2025-10-31 | 2025-10-31
| UAT Testing Sprint 5 | 2025-10-31 | 2025-11-03
| Production Release Sprint 5 | 2025-11-04 | 2025-11-04
| Go Live Support | 2025-11-04 | 2025-11-04
| Requiremet Gathering | 2025-10-27 | 2025-11-03
| Documentation Sign Off | 2025-11-03 | 2025-11-03
| BA UAC Review | 2025-11-04 | 2025-11-04
| QA writing test cases | 2025-11-04 | 2025-11-04
| QA Test cases review call | 2025-11-05 | 2025-11-05
| Quattro Support | 2025-10-17 | 2025-10-30
| Leave Pay and Gratutity Pay | 2025-10-28 | 2025-10-31
| BA UAC Review LP & GP | 2025-10-28 | 2025-10-28
| Test Cases Writing and Walthrough | 2025-10-28 | 2025-10-28
| Loan Request Integration FCB | 2025-11-03 | 2025-11-05
| QA Testing | 2025-10-27 | 2025-11-06
| Bug Fixing | 2025-11-05 | 2025-11-06
| Regression Testing | 2025-11-05 | 2025-11-05
Sprint 7 | Internal Demo Sprint 6 | 2025-11-06 | 2025-11-06
| BA UAT Testing Sprint 6 | 2025-11-07 | 2025-11-07
| External Demo Sprint 6 | 2025-11-07 | 2025-11-07
| UAT Testing Sprint 6 | 2025-11-07 | 2025-11-08
| Production Release | 2025-11-10 | 2025-11-10
| Go Live Support | 2025-11-10 | 2025-11-10
| Requiremet Gathering | 2025-11-10 | 2025-11-20
| Documentation Sign Off | 2025-11-21 | 2025-11-21
| BA UAC Call | 2025-11-11 | 2025-11-11
| QA Writing Testcases | 2025-11-11 | 2025-11-11
| QA Testcases Review Call | 2025-11-12 | 2025-11-12
| NAPSA Integration | 2025-11-18 | 2025-11-20
| Adding & Mapping of COA | 2025-11-11 | 2025-11-18
| Superadmin Access | 2025-11-19 | 2025-11-19
| Default Settings for the Statutory Components | 2025-11-11 | 2025-11-12
| Employee Upload History | 2025-11-13 | 2025-11-13
| Automatically add Pay Group | 2025-11-14 | 2025-11-14
| QA Testing | 2025-11-11 | 2025-11-20
| Bug Fixing | 2025-11-19 | 2025-11-20
| BA UAT Testing | 2025-11-20 | 2025-11-20
| Regression Testing | 2025-11-20 | 2025-11-20
| Internal Demo Sprint 7 | 2025-11-20 | 2025-11-20
| BA UAT Testing Sprint 7 | 2025-11-20 | 2025-11-21
| External Demo Sprint 7 | 2025-11-21 | 2025-11-21
| UAT Testing Sprint 7 | 2025-11-24 | 2025-11-25
| Production Release | 2025-11-26 | 2025-11-26
| Go Live Support | 2025-11-26 | 2025-11-26
Client Feedback Quattro
| Warranty Support | 2025-11-27 | 2025-12-16

## Risk and Dependencies
S No | Type | Description | Impact | Serverity | Owner | Probablility
1 | Requirement Gathering for sprint 2 | There can be a delay in the requiremnts as in the current sprint client had made some changes in the current scope as well | Timeline | High |  | Medium
2 | Chance of code conflict | There may be a chance of code conflicts or issues in the older modules due to the new add-ons in the existing system : if need to change on older module other nothing. | Timeline | Medium |  | Low
3 | Upcoming sprints are not finalized | There might be a chance that team can be idle as the upcoming sprint is not finalized. | Timeline | low |  | Medium
4 | No proper estimation | As we are working in a guesstimaae we cannot estimate the budget for eachsprint | Cost | Medium |  | High
5 |  |  | Timeline / Cost | Medium |  | High
6 |  |  | Timeline / Cost | Medium |  | High
7 |  |  | Timeline / Cost | Medium |  | Medium

## Sheet11 (hidden)
Requirement Description
1 | Department wise total earnings for netpay NAPSA,NHIMA & PAYE | Add total earnings for net pay, NAPSA, NHIMA, PAYE by department and for the total report at the end of the payslips | New Client Feedback | 1 | 3.2 | 0.8 | 4.8 | 3.2 | 2.8
3 | Leave Pay movement report |  |  | 2
5 | Reports for deductions by deduction type |  |  | 2
6 | Payroll and salary chnage approval shoul be twice | Add 2 approvals if needed for payroll approval and salary changes |  | 3
7 | Gratuity Report |  |  | 2
9 | Access/Zanaco bank integrations Download |  |  | 2
11 | Sick Leave Summary Report | A report that shows how many sick leaves someone has taken in a month/year |  | 3
12 | Email-Based Payroll Approval with Payslip Attachment | email that allows you to approve/reject payroll — currently, no payslip is attached. Need the draft payslip attached so the user can review and approve/reject directly from the email |  | 1
13 | simpler reporting on WageWorks for Stanbic transactions | EG: Chrometec OCT2025 wages” perhaps? | DIMITRI's Feedback
14 | make the payment section separate | make the payment section separate | Priyesh’s feedback
15 | Add a tab for employee history
16 | Add a from for contracs
17 | Add tempelates for termination letter,contracts,etc
20 | Remove approval when admin manually edits information
4 | Default earnings and deductions |  |  |  | Need to Check Feasibility
8 | Movement redundancy report
9 | Access/Zanaco bank integrations
10 | Notification when a contract expires | Notification when a contract expires